## Payment Schedule
PAYMENT SCHEDULE — KEEP MONEY IN A STEP AHEAD OF MONEY OUT
Walk one job down its stages BEFORE you sign it. Type what you spend at each stage and what you collect at each stage; the sheet tracks your running cash. When a stage flags red, your money-in fell behind your money-out — that stretch you're funding their job out of your own pocket. Fix it by collecting more, earlier.
↓ Rows 5–9 (yellow) are a filled-in EXAMPLE — a $40,000 job where a thin deposit leaves you funding the material week (watch the red flag). DELETE these rows before you plan your real job. ↓ | [5 empty] | THIS JOB
Job stage | Money OUT this stage $ | Payment due IN this stage $ | % of price | Running cash position | Flag | Job price (customer pays you): | 40000
Contract signed (deposit) | 0 | 6000 | 15% | 6000 |  | Total you'll bill in: | 40000
Material drop | 13000 | 0 | 0% | -7000 | YOU'RE FUNDING THE JOB | Payments check: | OK — covers the price
Tear-off done | 8000 | 18000 | 45% | 3000 |  | Total you'll spend out: | 29000
Dry-in complete | 6000 | 8000 | 20% | 5000 |  | On paper, left after costs: | 11000
Final walk / signoff | 2000 | 8000 | 20% | 11000 |  | Ever funding the job?: | YES — see red rows
TOTALS | 29000 | 40000 | 100% |  | OK — adds to job price
Deposit size, and whether you must hold it in a separate account, are set by YOUR state — this sheet doesn't decide that. Set your split so you cover your spend before you're ever out of pocket.
Commercial job with retainage? The customer parks a slice out of each payment until final signoff. Enter each milestone as what actually LANDS, then add a "Retainage released" stage row for the parked money — the amount and release date come from your contract, not a rule.